## week_24
Task list week - 24
Sr no. | Main task | Sub task | Numbers of days | Week 1 |  |  |  |  | status
|  |  |  | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-17 | 2023-06-18
1 | Terminator | platform creation | 2 | start | stop |  |  |  | In-progress
|  | project coding | 3 |  |  | start |  | stop | On Hold

## week_25
Task list week - 25
Sr no. | Main task | Sub task | Numbers of days | Week 25 | [5 empty] | status
|  |  |  | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-24
1 | Terminator | platform creation | 2 | 2023-06-23: END | In-progress
|  | project coding | 3 | 2023-06-24: START | In-progress
|  | Schematic review | 1 | [6 empty] | Done
2 | Drone mesurment | Full DSM system test | 2 | 2023-06-19: Start; 2023-06-20: END | Done
|  | Testing LORA module | 1 | 2023-06-21: START; 2023-06-22: END | Done
|  | Testing telimetry module | 1 | 2023-06-21: START; 2023-06-22: END | Done
3 | Cerbair | Cerbair pin mapping review | 1 | 2023-06-22: START; 2023-06-23: END | Done
|  | Adding EEPROM functionality into code | 1900-01-01 | 2023-06-23: START; 2023-06-24: END | In-progress